## Sheet1
Final Project Timeline
Planning | Oct. 17th - 21st | Oct. 24th - 28st | Oct. 31st - Nov. 4th | Nov. 7th - 11th | Nov. 14th - 18th | Nov. 21st - 25th | Nov. 28th - Dec. 2nd | Dec. 5th - 9th | Dec. 12th
Specification Document
Specification Revision
Design Document
Wire Circuit Components
Design Enclosure
Code LCD
Revise Previous Libaries For Components
Complete Must-Do Requirments
Encorperate Major & Minor Requirments
Debugging & Final Revision
Project Demonstration & Validation
Final Revised Design Document